## Sheet1
Task Name | Status (Not started, in progress, complete) | Person Responsible | Due Date | Task Details
Figure out what game engine | Completed | Team | 2016-02-22 | Decide what game engine to use (Unity)
Figure out Core Elements of Game | Not Started | Team | 2016-02-24 | Solidify details of what needs to be included in game
Assignment 1 Finished | Not Started | Team | 2016-02-26 | Learn tools needed
Look at Flour Sack Animation | Not Started | Team | 2016-02-26 | Learn animation techniques
Create main character (beer) and animations | Not Started | Jason Li, Songge Chen, David Lopez | 2016-02-29 | Have player textures and animations/movement done
Create room environment | Not Started | Dan, Linda, Ian | 2016-03-01 | Create the textures and layout for single room environment
Create obstacle/puzzle for room | Not Started | Team | 2016-03-04 | Create first puzzle/obstacle course for room
Create hallway environment | Not Started | Team | 2016-03-05 | Create textures and layout for hallway
Scale up room and hallway environments | Not Started | Team | 2016-03-06 | Combine room and hallway environments to make school layout
Assemble presentation | Not Started | Team | 2016-03-06 | Tie up all together in presentation